## Sheet1
Project Name - Sound Sensing at CU |  |  |  | 2019 | [11 empty] | 2009
|  |  |  | OCT |  |  |  | NOV |  |  |  | DEC
Deliverables |  | Owner | Duration | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Planning phase |  |  | 3 w
| Task I | All | 1 w
| Task II | All | 1 w
| Task III | All | 1 w
Team phase |  |  | 2 w
| Task I | Aidan O'Connor / Sam Sly | 1 w
| Task II | Bennett Miller, Kolin Newby, Ria Thakkar, Yi Wu | 1 w
Prototype phase |  |  | 2 w
| Task I | All | 1 w
| Task II | All | 1 w
Implementation phase/ Debug |  |  | 2 w
| Task I | All | 1 w
| Task II- Debug | Bennett Miller- Hardware Else- Software | 1 w
Closure phase |  |  | 1 w
| Task I | All | 1 w
Annotations |  |  |  | Planning Week 1 | Planning Week 2 | Planning Week 3 | Team Phase 1 | Team Phase 2 | Prototype Phase 1 | Prototype Phase 2 | Implementation Phase 1/Debug | Finalize Product/Show and Tell | Closure Phase
|  |  |  | Discuss Final Project Ideas | Finalize on which project | Discuss Scheduling/ Roles | Order Parts Required | Begin Testing Parts | Discuss Final Prototype(Hardware) | Discuss Final Prototype (software) | Hardware and Software combination | Finalize Product and Debug/ Repeat | Turn in final documents
Group Members: | Aidan O'Connor | Bennett Miller | Kolin Newby | Ria Thakkar | Sam Sly | Yi Wu
Week 1: | Come up with 1 project idea each | Come up with 1 project idea each | Come up with 1 project idea each | Come up with 1 project idea each | Come up with 1 project idea each | Come up with 1 project idea each
Week 2: | Vote on Project Ideas | Vote on Project Ideas | Vote on Project Ideas | Vote on Project Ideas | Vote on Project Ideas | Vote on Project Ideas | Vote on Project Ideas
Week 3: | Chosen Role: Software- Math/Graphs | Chosen Role: Hardware- Find and figure out which sound sensor would be ideal | Chosen Role: Software- Online Database | Chosen Role: Software- Online Database | Chosen Role: Software- Hardware/Software Integration | Chosen Role: Software- Hardware/Software Integration
Week 4: | Order Parts | Find best sound sensor | Begin Database Research | Begin Database Research | Order Parts | Begin Database/ Python Integration
Week 5: | Write Basic Python Scripts to parse and display data | Figure out how to export serial data(sound in dB) | Begin Writing Database Backend | Begin Writing Database Backend | Begin Writing Database Frontend | Take data to display on website(rough form)
Week 6: | Show final display preference- Graphs/ Raw data etc | Finalize data output over serial terminal via RPI/Arduino | Figure out how to take data from RPI to hold in database | Figure out how to take data from RPI to hold in database | Make website display things nicely | Figure out best way to display data
Week 7: | Debug Graphs/ Display information | Debug Final Hardware | Debug arduino/RPI data | Debug Database Backend | Debug Database frontend | Debug Database backend/frontend
Week 8: | Verify Graphs Display information properly | Verify hardware data is accurate and works as intended | Verify Backend works- no erroneous data | Verify Backend works- no erroneous data | Verify Frontend looks nice(website) | Verify everything works as intended together
Week 9: | Make sure my part of project is complete | Make sure my part of project is complete | Make sure my part of project is complete | Make sure my part of project is complete | Make sure my part of project is complete | Make sure my part of project is complete
Week 10: | Turn in docs | Turn in docs | Turn in docs | Turn in docs | Turn in docs | Turn in docs
** Note that dates correspond to Friday of this week. Meaning that everything needs to be done by Friday at the latest